## Slide 1: Project Management
Chapter 17: Project Implementation Overview

## Slide 2: Project Implementation Overview
Definition
Directing the Work
Change Control

## Slide 3: Implementation Phase
Also known as Project Execution
Implementation follows Project Planning phase
PM follows the plan and handles any problems that arise
Actual work is done to produce the deliverables
Project change requests are managed

## Slide 4: The project manager during implementation
Produce the deliverables
Control quality
Manage project team performance
  Determine how to measure
  Measure
  Provide feedback and support
Change control

## Slide 5: Change Control
Changes may change
  the scope
  a planned process
  the schedule
Ensure you have developed a change control process during the project planning phase

## Slide 6: Change Control Process
Usually consists of
  Change request (use a form)
  Review and approval process
  Tracking system

## Slide 7: Schedule compression
A requirement to deliver sooner than identified in the original schedule, or to make up for project delays.
Two options:
  Crashing
  Fast-tracking
Not free of costs and risks

## Slide 8: Schedule compression
Crashing
  Add more resources to a critical task to try to speed it up
  Always costs more
  Does not always work

## Slide 9: Schedule compression
Fast tracking
  Activities that were planned to do in sequence, modify to do them in parallel
  Adds to project risk
  May increase need to redo some work

## Slide 10: Implementation Phase Completion
Deliverables constructed
Customer has accepted
Review the phase to determine if the project is ready for closure

## Slide 11: Implementation phase summary
Follow the plans made in the planning phase
Manage problems
Manage change requests and changes
Schedule compression:
  Crashing
  Fast tracking
Implementation phase completion

## Slide 12: QUESTIONS?