## Slide 1: Chapter 6 – Project Schedule Management
Direct quotes from source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Prepared by: Celeste Ng,
Last updated: April, 2024
專案進度管理

## Slide 2: Project Management Framework
10 Project Management Knowledge Areas:
Project Scope Management
Project Schedule Management
Project Cost Management
Project Quality Management
Project Resource Management
Project Communications Management
Project Risk Management
Project Procurement Management
Project Stakeholder Management
Project Integration Management
5 process groups
Designed by: @CelesteSPNg, 2024

## Slide 3: Learning Objectives
Project Schedule Management Processes
Project Schedule Management Processes
  Input
  Tools & Techniques
  Outputs

## Slide 4: The Project Schedule Management processes
6.1 Plan Schedule Management
6.2 Define Activities
6.3 Sequence Activities
6.4 Estimate Activity Durations
6.5 Develop Schedule
6.6 Control Schedule

## Slide 5: The Project Schedule Management processes
6.1 Plan Schedule Management—The process of establishing the policies制定政策, procedures, and documentation for planning, developing, managing, executing, and controlling the project schedule.
6.2 Define Activities—The process of identifying and documenting the specific actions to be performed記錄具體的行動to produce the project deliverables.
6.3 Sequence Activities—The process of identifying and documenting relationships among the project activities.
6.4 Estimate Activity Durations—The process of estimating the number of work periods估算工作週期的數量needed to complete individual activities with the estimated resources.
6.5 Develop Schedule—The process of analyzing activity sequences, durations 長短, resource requirements, and schedule constraints to create the project schedule model時間表模型for project execution and monitoring and controlling.
6.6 Control Schedule—The process of monitoring the status of the project to update the project schedule and manage changes to the schedule baseline.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
規劃進度管理
定義專案活動
排序專案活動
估計專案活動持續時間
制定時間表
控制進度

## Slide 6: Project Management Process Groups and Knowledge Areas Mapping (1)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
There are processes from each knowledge area under the “planning” and “monitoring and controlling” process groups.
“planning”
“monitoring and controlling”
Reminder

## Slide 7: Project Schedule Management overview
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Schedule baseline -進度基線

## Slide 8: 6.1 PLAN SCHEDULE MANAGEMENT (1): ITTOs, Inputs
The key benefit of this process is that it provides guidance and direction on how the project schedule will be managed throughout the project. (提供指導和方向)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 9: 6.1 PLAN SCHEDULE MANAGEMENT (2): Inputs
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Enterprise environmental factors:
Organizational culture and structure,
Team resource availability and skills and physical resource availability,
Marketplace conditions,
Financial considerations,
Social influences
Organizational process assets:
Historical information and lessons learned repositories;
Existing formal and informal schedule development, policies, procedures, and guidelines;
Templates 樣本 and forms; and
Monitoring and reporting tools

## Slide 10: 6.1 Schedule management plan contents: Outputs
Project schedule model development. The scheduling methodology and the scheduling tool to be used
Level of accuracy. The level of accuracy … used in determining realistic activity duration estimates and may include an amount for contingencies. (用於確定實際活動持續時間估計)
Units of measure. Each unit of measurement計量單位(such as staff hours, staff days, or weeks for time measures) is defined for each of the resources.
Organizational procedures links. The work breakdown structure (WBS) … the framework for the schedule management plan …
Project schedule model maintenance. The process used to update the status and record progress of the project in the schedule model .
Control thresholds控制進度的門檻/閾值. Variance thresholds for monitoring schedule performance may be specified to indicate an agreed-upon amount of variation to be allowed ... (允許的變更量)
Rules of performance measurement. Earned value management掙Zhèng值管理(EVM) rules or other physical measurement rules of performance measurement are set. For example, the schedule management plan may specify:
  Rules for establishing percent complete,
  EVM techniques (e.g., baselines, fixed-formula, percent complete, etc.) to be employed (for more specific information, refer to the Practice Standard for Earned Value Management [17]), and
  Schedule performance measurements such as schedule variance (SV) and schedule performance index (SPI) used to assess the magnitude of variation to the original schedule baseline.
Reporting formats報告格式. The formats and frequency for the various schedule reports are defined.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 11: 6.1 Schedule management plan contents: Outputs

## Slide 12: 6.2 DEFINE ACTIVITIES (1): ITTOs, Inputs
The key benefit of this process is that it decomposes work packages into schedule activities that provide a basis for estimating估算的基礎, scheduling, executing, monitoring, and controlling the project work. (分解工作包進入計劃活動，提供估算的基礎)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Rolling wave planning is an iterative planning technique迭Dié代計劃技術in which the work to be accomplished in the near term is planned in detail, while work further in the future is planned at a higher level. It is a form of progressive elaboration
applicable to work packages

## Slide 13: 6.2 DEFINE ACTIVITIES
Project charter, schedule management plan, scope baseline
User stories
Features/ Epics
Activities

## Slide 14: 6.2 DEFINE ACTIVITIES (2): Outputs
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Scope baseline. --- includes:
the project WBS, deliverables, constraints, and assumptions
[previously set]

## Slide 15: 6.3 SEQUENCE ACTIVITIES (1): ITTOs, Inputs
The key benefit of this process is that it defines the logical sequence of work定義工作的邏輯順序to obtain the greatest efficiency given all project constraints.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Precedence Diagramming Method優先圖法

## Slide 16: 6.3 SEQUENCE ACTIVITIES (2): Inputs
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Scope baseline. --- includes:
the project WBS, deliverables, constraints, and assumptions
[previously set]

## Slide 17: 6.3 Precedence Diagramming Method優先圖法 (PDM) (1): Tools
The precedence diagramming method (PDM) is
  A technique used for constructing a schedule model (用於構建進度模型的技術)
  Activities are represented by nodes (活動由節點表示)
  Are graphically linked by one or more logical relationships to show the sequence in which the activities are to be performed.
  A predecessor activity前任活動is an activity that logically comes before a dependent activity相關活動in a schedule.
  A successor activity後繼活動is a dependent activity that logically comes after another activity in a schedule.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 18: 6.3 Precedence Diagramming Method優先圖法(PDM) (2)
The PDM includes four types of dependencies or logical relationships. They are:
  Finish-to-start (FS). A logical relationship in which a successor activity cannot start until a predecessor activity has finished.
  Finish-to-finish (FF). A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. For example,
  Start-to-start (SS). A logical relationship in which a successor activity cannot start until a predecessor activity has started. For example
  .
  Start-to-finish (SF). A logical relationship in which a successor activity cannot finish until a predecessor activity has started.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Ex.: PC hardware is assembled (predecessor)  PC (successor) operating system is installed
Ex.: writing a document (predecessor) is required to finish before ---- editing the document (successor) can finish
Ex.: level concrete (successor) cannot begin until --- pour foundation (predecessor) begins直到澆築基礎開始混凝土才能開始

## Slide 19: 6.3 Precedence Diagramming Method優先圖法(PDM) (3)
FS is the most commonly used type of precedence relationship.
The SF relationship is very rarely used, but is included to present a complete list of the PDM relationship types.
Two activities can have two logical relationships at the same time (for example, SS and FF). Multiple relationships between the same activities are not recommended, so a decision has to be made to select the relationship with the highest impact.
Closed loops閉環are also not recommended in logical relationships
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 20: 6.3 Precedence Diagramming Method優先圖法(PDM) (3)
FS: boil water, brew coffee
SS: boil water, prepare cups
SF: (rare) boil water, brew coffee (???)
FF: commercial break, brew coffee
coffee time
Photo credit: https://www.acouplecooks.com/how-to-make-coffee-methods/

## Slide 21: 6.3 DEPENDENCY DETERMINATION AND INTEGRATION (1)
Dependencies依賴關係may be characterized by the following attributes: mandatory or discretionary, internal or external. FOUR types of dependencies are
(1) Mandatory dependencies 強制性的依賴關係.
  Mandatory dependencies are those that are legally or contractually required or inherent in the nature of the work. (法定的或者約定要求或固有工作性質的依賴關係)
  Mandatory dependencies often involve physical limitations, … are sometimes referred to as hard logic or hard dependencies.
(2) Discretionary dependencies 自由性的依賴關係.
  Discretionary dependencies are sometimes referred to as preferred logic, preferential logic, or soft logic.
  Discretionary dependencies are established based on knowledge of best practices within a particular application area or some unusual aspect of the project where a specific sequence is desired, even though there may be other acceptable sequences.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Air conditioner installation & curtain installation
A prototype has to be built  before it can be tested

## Slide 22: 6.3 DEPENDENCY DETERMINATION AND INTEGRATION (2)
(3) External dependencies 外部的依賴關係.
  External dependencies involve a relationship between
    Project activities & non-project activities.
  These dependencies are usually outside of the project team’s control.
(4) Internal dependencies 外部的依賴關係.
  Internal dependencies involve a precedence relationship between project activities and are generally inside the project team’s control.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Testing activity in a software project dependent on …. the delivery of hardware (from an external source)
Team cannot test a machine until they assemble it

## Slide 23: 6.3 LEADS AND LAGS (1)
A lead is
  the amount of time a successor activity can be advanced with respect to a predecessor activity後繼活動可以相對於前任活動提前的時間量
  Lead is often represented as a negative value for lag in scheduling software
A lag is
  the amount of time a successor activity will be delayed with respect to a predecessor activity.
  Lag is often represented as a positive value
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
e.g. of “lead”: FS -2
e.g. of “lag”: FS +2

## Slide 24: 6.4 ESTIMATE ACTIVITY DURATIONS (1)
The key benefit of this process is that it provides the amount of time each activity will take to complete.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 25: 6.4 ESTIMATE ACTIVITY DURATIONS (2)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 26: 6.4 ESTIMATE ACTIVITY DURATIONS (3)
Factors for consideration when estimating duration估算時間考慮的因素include:
Number of resources. Increasing the number of resources to twice the original number of the resources does not always reduce the time by half, as it may increase extra duration due to
  Risk, knowledge transfer, learning curve （學習曲線-表示獲得熟練技巧的進步過程需要花時間的), additional coordination, and other factors involved.
Advances in technology.
  For example, an increase in the output of a manufacturing plant may be achieved by procuring the latest advances in technology, which may impact duration and resource needs.(技術進步 -增加產量)
Motivation of staff. The project manager also needs to be aware of
  Student Syndrome—or procrastination— when people start to apply themselves only at the last possible moment before the deadline, and
  Parkinson’s Law where work expands to fill the time available for its completion.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 27: 6.4 TOOLS AND TECHNIQUES (1)
(1) ANALOGOUS ESTIMATING 類比估計法:
Estimating the duration or cost of an activity or a project using historical data from a similar activity or project. (使用來自類似活動或項目的歷史數據)
Is frequently used to estimate project duration when there is a limited amount of detailed information about the project.
Is generally less costly and less time-consuming than other techniques, but it is also less accurate.
(2) PARAMETRIC ESTIMATING參數估計法:
Parametric estimating is an estimating technique in which an algorithm is used to calculate cost or duration based on historical data and project parameters. (統計算法)
This technique can produce higher levels of accuracy depending on the sophistication and underlying data built into the model.
Parametric schedule estimates can be applied to a total project or to segments of a project, in conjunction with other estimating methods.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 28: 6.4 TOOLS AND TECHNIQUES (2)
(3) THREE-POINT ESTIMATING三點估計法:
The accuracy of single-point duration estimates may be improved by considering estimation uncertainty and risk. (考慮估計不確定性和風險)
Using three-point estimates helps define an approximate range for an activity’s duration (定義活動持續時間的範圍):
  Most likely (Mₜ). This estimate is based on the duration of the activity, given the resources likely to be assigned, their productivity, realistic expectations of availability for the activity, dependencies on other participants, and interruptions.
  Optimistic (Oₜ). The activity duration based on analysis of the best-case scenario for the activity.
  Pessimistic (Pₜ). The duration based on analysis of the worst-case scenario for the activity.
Depending on the assumed distribution假定分佈of values within the range of the three estimates, the expected duration, E, can be calculated. One commonly used formula is triangular distribution:
  Eₜ = (Oₜ + Mₜ + Pₜ) / 3.
Triangular distribution is used when there is insufficient historical data or when using judgmental data.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 29: 6.4 ESTIMATE ACTIVITY DURATIONS
Two popular “three-point estimates ” formula:
1. Triangular distribution:
  Triangular Distribution: E = (o + m + p ) / 3
  where E is Estimate; o = optimistic estimate; p = pessimistic estimate; m = most likely estimate
2. Beta (or PERT):
  Beta Distribution (PERT): E = (o + 4m + p ) / 6
  The beta distribution is a weighted average in which more weight is given to the most likely estimate.
  This alteration to the formula and placing more weight on the most likely estimate is made to increase the accuracy of the estimate by making it follow the Normal Distribution shape.
  Hence, in most of the cases, the Beta (PERT) distribution has been proven to be more accurate than the 3-Point triangular estimation.
The variance is obtained by the difference between the pessimistic and the optimistic forecast divided by six
Standard deviation = (p – o)/ 6
Source: https://www.projectmanagement.com/wikis/368763/3-Points-Estimating
Photo credit: https://medium.com/analytics-vidhya/normal-distribution-54eca3a63a77

## Slide 30: 6.4 TOOLS AND TECHNIQUES (3)
(4) BOTTOM-UP ESTIMATING 自下而上的估算法:
Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS
(5) DATA ANALYSIS - Reserve analysis 儲備分析法
Reserve analysis is used to determine the amount of contingency and management reserve needed for the project.
  Contingency reserves應急儲備 are the estimated duration within the schedule baseline, which is allocated for identified risks that are accepted.
    Contingency reserves are associated with the known-unknowns, which may be estimated to account for this unknown amount of rework.
  Management reserves are a specified amount of the project budget withheld for management control purposes and are reserved for unforeseen work that is within scope of the project.
    Management reserves are intended to address the unknown-unknowns that can affect a project.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 31
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
6.4 BOTTOM-UP ESTIMATING:
WBS – Decomposition by Phase

## Slide 32: 6.4 ESTIMATE ACTIVITY DURATIONS

## Slide 33: 6.5 DEVELOP SCHEDULE (1)
The key benefit of this process is that it generates a schedule model with planned dates for completing project activities. (建立時間表模型)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 34: 6.5 DEVELOP SCHEDULE (2)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 35: 6.5 TOOLS AND TECHNIQUES (1) - CPM
CRITICAL PATH METHOD (CPM)關鍵路徑法:
The critical path method is used to
  Estimate the minimum project duration and
  Determine the amount of schedule flexibility on the logical network paths within the schedule model.
This schedule network analysis technique calculates the:
  Early start, early finish, late start, and late finish dates for all activities
  Without regard for any resource limitations by performing a forward and backward pass analysis through the schedule network,
The longest path on a network diagram … is the critical path.
The critical path is the sequence of activities that represents the longest path through a project, which determines the shortest possible project duration.
The longest path has the least total float—usually zero.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 36: 6.5 TOOLS AND TECHNIQUES (1) - CPM
the total float or schedule flexibility is measured by:
  the amount of time that a schedule activity can be delayed or extended from its early start date without delaying the project finish date or violating a schedule constraint.
  A critical path is normally characterized by zero total float on the critical path.
the free float is the amount of time that
  a schedule activity can be delayed without delaying the early start date of any successor or violating a schedule constraint.
  For example the free float for Activity B, in Figure 6-16, is 5 days.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 37
ES
DUR
EF
TASK ID
LS
TF
LF
ES = Earliest Start
DUR = Duration
EF = Earliest Finish
LS = Latest Start
TF = Total Float
LF = Latest Finish
3
TASK A
Use red arrows to illustrate the critical path.
5
TASK B
CRITICAL PATH DIAGRAM – An example of calculation
Critical Path Diagram Template – obtained from: Smartsheet, URL - https://www.smartsheet.com/content/critical-path-templates

## Slide 38
ES
DUR
EF
TASK ID
LS
TF
LF
ES = Earliest Start
DUR = Duration
EF = Earliest Finish
LS = Latest Start
TF = Total Float
LF = Latest Finish
0
3
3
TASK A
0
0
3
Use red arrows to illustrate the critical path.
3
5
8
TASK B
3
0
8
CRITICAL PATH DIAGRAM – An example of calculation
Critical Path Diagram Template – obtained from: Smartsheet, URL - https://www.smartsheet.com/content/critical-path-templates
Total Float = LS-ES or LF-EF

## Slide 39
ES
DUR
EF
TASK ID
LS
TF
LF
2
TASK A
ES = Earliest Start
DUR = Duration
EF = Earliest Finish
LS = Latest Start
TF = Total Float
LF = Latest Finish
1
TASK E
3
TASK B
4
TASK C
5
TASK D
Use red arrows to illustrate the critical path.
3
TASK F
CRITICAL PATH DIAGRAM – Your final exam question
Critical Path Diagram Template – obtained from: Smartsheet, URL - https://www.smartsheet.com/content/critical-path-templates
Forward pass, select the MAX value of a predecessor’s EF
Backward pass, select the MIN value of successor’s LS
Total Float = LS-ES or LF-EF

## Slide 40: 6.5 DEVELOP SCHEDULE: critical path method
Total Float = LS – ES or LF - EF
Free Float = ES (successor) – EF (current) + 1
The Free Float and the Total Float of a critical activity are = ZEROs

## Slide 41: 6.5 TOOLS AND TECHNIQUES (2) – Res Opt
(2) RESOURCE OPTIMIZATION 資源優化:
Examples of resource optimization techniques that can be used to adjust the schedule model :
  Resource leveling資源平衡. A technique in which start and finish dates are adjusted
    based on resource constraints with the goal of balancing the demand for resources with the available supply根據資源限制進行調整，以平衡資源需求與可用供應之間的平衡.
    Is used when required resources are
      available only at certain times or in limited quantities, or
      over allocated, such as when a resource has been assigned to two or more activities during the same time period (as shown in Figure 6-17), or
      OBJECTIVE: there is a need to keep resource usage at a constant level.
    Resource leveling can often cause the original critical path to change. Available float is used for leveling resources. Consequently, the critical path through the project schedule may change.
  Resource smoothing資源平滑. A technique that adjusts the activities of a schedule model such that
    OBJECTIVE: the requirements for resources on the project do not exceed certain predefined resource limits.
    In resource smoothing, as opposed to resource leveling, the project’s critical path is not changed and the completion date may not be delayed.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 42: 6.5 TOOLS AND TECHNIQUES (2) – Res Opt
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Keep resource usage at a constant level  8 Hrs
Keep resource usage at a predefined “limit”
Photo credit: https://pm-training.net/resource-leveling-vs-resource-smoothing/

## Slide 43: 6.5 DEVELOP SCHEDULE: resource optimization

## Slide 44: 6.5 TOOLS AND TECHNIQUES (3) – Sch Comp
(3) SCHEDULE COMPRESSION 時間壓縮:
Schedule compression 時間壓縮 techniques are used to shorten or accelerate the schedule duration用於縮短或加快計劃時間 without reducing the project scope in order to meet schedule constraints, imposed dates, or other schedule objectives.
Schedule compression techniques are:
  Crashing. A technique used to shorten the schedule duration for the least incremental cost by adding resources.
    Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path.
    Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration.
    Does not always produce a viable alternative and may result in increased risk and/or cost.
  Fast tracking. A schedule compression technique in which activities or phases normally done in sequence
    Fast tracking may result in rework, and increased risk and project costs.
    Fast tracking only works when activities can be overlapped to shorten the project duration on the critical path.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 45: 6.5 TOOLS AND TECHNIQUES (3) – Sch Comp
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
Both happen on the “critical path”
Overlap activities
Add resources

## Slide 46: 6.5 DEVELOP SCHEDULE: compression techniques

## Slide 47: 6.5 TOOLS AND TECHNIQUES (4) – Agile
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.
(4) AGILE RELEASE PLANNING 敏捷版本發布規劃:
provides a high-level summary timeline of the release schedule (typically 3 to 6 months) … and also determines the number of iterations or sprints in the release
Prod. Roadmap  Release Plan

## Slide 48: 6.5 Project Schedule Presentation
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 49: 6.6 CONTROL SCHEDULE (1)
The key benefit of this process is that the schedule baseline is maintained進度基準得以維持throughout the project.
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 50: 6.6 CONTROL SCHEDULE (2)
Source: PMI, 2017, “A guide to the project management body of knowledge (PMBOK guide),” Sixth edition, Newtown Square, PA: Project Management Institute, Inc.

## Slide 51
Recap today’s lecture – Summary
Describe an overall framework for project schedule management專案時間管理的總體架構
  process & practices, inputs, outputs, tools & techniques
  6.1 Plan Schedule Management
  6.2 Define Activities
  6.3 Sequence Activities
  6.4 Estimate Activity Durations
  6.5 Develop Schedule
  6.6 Control Schedule
(6.1 Plan Schedule Management – tool) – E, M, D/a (alternative anal.)
(6.2 Define Activities – tool) – E, M, Roll W P, decomposition
(6.3 Sequence Activities – Tool + Output ) – T: PDM, dependency deter., leads & lags; O: project schedule network diagram
(6.4 Estimate Activity Durations – tool) – T: Analo, Para, 3-point, bottom, data
(6.5 Develop Schedule – tool) – T: CPM (free float + total float), Res opt., sch comp.,
(6.6 Control Schedule – tool)

## Slide 52
THANK YOU!
Celeste SP Ng
Phone: 2614
Email: celeste@saturn.yzu.edu.tw
Website: http://celesteng.mis.yzu.edu.tw/